DATE:		SEPTEMBER 24, 2024

DEPARTMENT: 	FINANCE

FROM:	            RENE MENDEZ, CITY MANAGER

BY:                             JIM PIA, ASSISTANT CITY MANAGER

SELINA ANDREWS, ACTING FINANCE DIRECTOR

ABE PEDROZA, SENIOR FINANCE MANAGEMENT ANALYST

TITLE:	AMERICAN RESCUE PLAN ACT (ARPA) PROJECTS UPDATE

RECOMMENDATION:

A motion to approve a resolution delegating authority to the City Manager to reallocate American Rescue Plan Act funding between various programs and projects previously approved by City Council.

EXECUTIVE SUMMARY:

The recommendation provides authority to reallocate funding between ARPA projects in accordance with the U.S. Treasury Department regulations to mitigate the risk of not having funds encumbered by the December 31, 2024, deadline. The recommended action will not impact any services or projects previously authorized by the City Council and will result in the obligation of all ARPA Funds prior to the deadline.

BACKGROUND:

On March 11, 2021, President Biden signed the American Rescue Plan Act, which provided the City with $51,567,313 in relief funds.  These additional resources have provided critical community and economic recovery support.

ARPA requires that local governments obligate all ARPA funds (e.g., encumber funding through the issuance of contracts/purchase orders) by December 31, 2024, and to expend all ARPA funds by December 31, 2026.  Due to this timeline, a number of the community and economic recovery workstreams were anticipated to be spent over a multi-year period.  Of the $51.6 million initially received ARPA funding, a remaining amount of $25.6 million is included in the FY 2024-25 Budget. While the City has made considerable progress in this effort, a total of $12,682,496.37 remain unencumbered as of September 2024 as detailed below.

| Dept | Project | Original Budget | Approved Amend | Amended Budget | Actuals to Date | FYTD 24-25 Enc | Remaining | % Used |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CD | 3220 SHARE Center | 1,000,000 | - | 1,000,000 | 1,000,000 | - | - | 100% |
| CD | 8161 Chinatown Navigation Center | 1,000,000 | - | 1,000,000 | 775,058 | 212,528 | 12,414 | 99% |
| CD | 8162 Homeless Motel Program | 3,000,000 | - | 3,000,000 | 2,122,494 | - | 877,506 | 71% |
| CD | 9021 Housing Production Fund | 7,000,000 | - | 7,000,000 | 5,800,303 | 268,794 | 930,903 | 87% |
| CD | 9181 Downtown Streets Team | 600,000 | - | 600,000 | 388,396 | 215,996 | (4,392) | 101% |
| Fire | 9235 Fire Station Renovations | 1,500,000 | - | 1,500,000 | 427,132 | 9,407 | 1,063,461 | 29% |
| Fire | 9541 Fire Station Repairs | 1,400,000 | - | 1,400,000 | 89,488 | 119,100 | 1,191,413 | 15% |
| PW | 8170 City Hall / Facility HVAC | 5,002,313 | 2,000,000 | 7,002,313 | 4,357,248 | 2,954,968 | (309,903) | 104% |
| PW | 8180 Street Repair & Traffic Safety | 6,000,000 | - | 6,000,000 | 4,272,224 | 1,073,281 | 654,494 | 89% |
| PW | 8190 Sewer System Work | 4,620,000 | 354,539 | 4,974,539 | 200,240 | 638,653 | 4,135,645 | 17% |
| PW | 8192 Stormwater Green Infra | 3,000,000 | (230,678) | 2,769,322 | 911,181 | 1,008,129 | 850,011 | 69% |
| PW | 9086 Natividad Creek Silt | 1,545,000 | (1,062,000) | 483,000 | - | 332,325 | 150,675 | 69% |
| PW | 9293 Stormwater Master Plan | 800,000 | - | 800,000 | 794,448 | 5,552 | - | 100% |
| PW | 9720 Sidewalk & Drainage Impr | 6,000,000 | - | 6,000,000 | 5,134,942 | 237,289 | 627,769 | 90% |
| PW | 9727 Gabilan Creek Silt | 500,000 | (61,861) | 438,139 | 236,473 | 49,394 | 152,273 | 65% |
| LCS | 8171 Playground & Closter Park Impr | 2,000,000 | 1,000,000 | 3,000,000 | 975,644 | 259,988 | 1,764,367 | 41% |
| LCS | 8191 Park Irrigation Updates | 5,000,000 | (4,000,000) | 1,000,000 | 406,174 | 65,028 | 528,798 | 47% |
| LCS | 9165 Hebbron Family Center Impr | 1,500,000 | 2,000,000 | 3,500,000 | 349,005 | 3,150,995 | - | 100% |
| LCS | 9311 Firehouse Rec Center | 100,000 | - | 100,000 | 34,867 | 8,071 | 57,063 | 43% |
|  | TOTAL | 51,567,313 | - | 51,567,313 | 28,275,317 | 10,609,499 | 12,682,496 | 75% |

Over the last few of months, staff developed timelines for all projects and has determined that the reallocation of funding for certain projects is necessary to meet program needs while adhering to the December 31, 2024, encumbrance deadline.

An example of what the reallocation of projects might look like is if any specific project identified in the table above does not get to a point where a contract is in place to allow the funds to be encumbered, the City Manager may look at other projects that already have contracts in place such as Street Repair & Traffic Safety and authorize additional funds to be encumbered there. This will allow for projects to continue moving forward with ARPA monies.

Should the encumbrance deadline not be met, ARPA allows for governments to reimburse themselves for lost revenue due to the pandemic, and then use that revenue to pay for government services. In accordance with regulations provided by the U.S. Treasury Department, the City’s calculated revenue loss (calculated across all eligible City funding sources) exceeds the $12.7 million in unencumbered ARPA allocated across several services and projects. The City may decide to allocate any and all relief funds to this purpose, which would present the opportunity to shift already programmed general fund resources to complete the projects.

While we expect to be able to encumber the funds, we will bring back a report detailing the final results, including any reallocation and/or reimbursement of revenue.

CEQA CONSIDERATION:

Not a Project.  The City of Salinas has determined the proposed action is not a project as defined by the California Environmental Quality Act (CEQA) (CEQA Guidelines Section 15378).

CALIFORNIA GOVERNMENT CODE §84308 APPLIES:

No.

STRATEGIC PLAN INITIATIVE:

The projects and programs funded by the Salinas Recovery Plan under the American Rescue Plan Act (ARPA) of 2021 achieves the Council 2022-2025 Strategic Goals of Housing/Affordable Housing, Infrastructure and Environmental Sustainability, Public Safety, Youth and Seniors, and Effective and Culturally Responsive Government.

DEPARTMENTAL COORDINATION:

This staff report has been coordinated with the City Manager’s Office, Finance Department, Community Development, Fire, Public Works, and Library & Community Services.

FISCAL AND SUSTAINABILITY IMPACT:

American Rescue Plan Act (ARPA) funding allows the City to move forward with several important projects and programs with no impact on the City’s General Funds. Reallocation of ARPA funds is not being recommended at this time. However, as it gets closer to the encumbrance deadline, the City Manager may need to reallocate funding as necessary to avoid the City losing ARPA monies.

| Fund | Appropriation | Appropriation /Project Name | Total Appropriation | Amount for recommendation | FY 24-25 Operating Budget Page | Last Budget Action (Date, Resolution)* |
| --- | --- | --- | --- | --- | --- | --- |
| 3911 | 30.3220 | Housing & Com Dev (SHARE) | $1,000,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 30.8161 | Chinatown Nav Center Op | $1,000,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 30.8162 | Salinas Homeless Motel Program | $3,000,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 30.9021 | Housing Production Fund | $7,000,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 30.9181 | Downtown Streets Team | $600,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 45.9235 | Fire Station Renovations | $1,500,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 45.9541 | Fire Station Repairs | $1,400,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 50.8170 | Adapt to City Hall & Fac HVAC | $7,002,313 | $0 | n/a | 11/16/21,22250 12/05/23,22860 04/23/24,22950 |
| 3911 | 50.8180 | Street Repair / Traffic Safety | $6,000,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 50.8190 | Sewer System Work | $4,974,539 | $0 | n/a | 11/16/21,22250 08/20/24,23073 |
| 3911 | 50.8192 | Stormwater Green Infra | $2,769,322 | $0 | n/a | 11/16/21,22250 08/20/24,23073 |
| 3911 | 50.9086 | Natividad Creek Silt Removal | $483,000 | $0 | n/a | 11/16/21,22250 04/23/24,22950 08/20/24,23073 |
| 3911 | 50.9293 | Storm Water Master Plan Upd | $800,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 50.9720 | Sidewalk & Drainage Impr | $6,000,000 | $0 | n/a | 11/16/21,22250 |
| 3911 | 50.9727 | Gabilan Creek Silt Removal | $438,139 | $0 | n/a | 11/16/21,22250 08/20/24,23073 |
| 3911 | 55.8171 | Playground & Closter Park Impr | $3,000,000 | $0 | n/a | 11/16/21,22250 06/18/24,23016 |
| 3911 | 55.8191 | Park Irrigation Updates | $1,000,000 | $0 | n/a | 11/16/21,22250 12/05/23,22860 03/05/24,22911 06/18/24,23016 |
| 3911 | 55.9165 | Hebbron Family Center Impr | $3,500,000 | $0 | n/a | 11/16/21,22250 03/05/24,22911 |
| 3911 | 55.9311 | Firehouse Rec Center | $100,000 | $0 | n/a | 11/16/21,22250 |

ATTACHMENTS:

- Resolution

- PowerPoint