AGREEMENT —AMENDMENT NO. 1 TO

FISCAL YEAR 2023-24

HCD 2022 ESG

SUBRECIPIENT FUNDING AGREEMENT

BETWEEN CITY OF SALINAS

AND

CENTRAL COAST CENTER FOR INDEPENDENT LIVING

FOR THE

CCCIL RAPID REHOUSING AND HOUSING STABILIZATION PROGRAM

Agreement No. 22SESG01

This Amendment No. 1 (“Amendment”) to the Subrecipient Funding Agreement (“Agreement”) is entered into this 18th day of June 2024, by and between the City of Salinas (“City”) and Central Coast Center for Independent Living (“CCCIL”), a California non-profit corporation, (“Subrecipient”). City and Subrecipient may be individually referred to herein as a “Party” and collectively the City and Subrecipient may be referred to as the “Parties.”

RECITALS

WHEREAS, the City and CCCIL first entered into an HCD 2022 ESG Subrecipient Funding Agreement (Agreement) effective this 1st day July 2023, pursuant to which CCCIL agreed to act as and provide certain services for compensation; and

WHEREAS, there was a delay the implementation of services for compensation and the city assessed the State expenditure requirements to determine if all funds would be spent by June 30, 2024; the city solicited feedback on the Subrecipients ability to expend the funds; and

WHEREAS, CCCIL notified the City of their inability to fully spend all the HCD ESG 2022 funds by June 30, 2024, and the city determined a partial reallocation of funds was necessary; and

WHEREAS, the City and Subrecipient desire to amend the Agreement to extend the term of the agreement to October 31, 2024, and to reduce the maximum compensation from the original funding agreement amount of $133,284.00 by $65,000, with a compensation not to exceed $68,284;

NOW, THEREFORE, in mutual consideration of the terms and conditions set forth below, the Parties agree as follows:

TERMS

- The Agreement, Section 2, Term and Section 4. Funding section, is amended to restate in its entirety the following:

Section 2. Term:

This Agreement shall commence on July 1, 2023, and expires on October 31, 2024, unless suspended or terminated sooner pursuant to the terms of this Agreement. This Agreement may not be extended beyond the term set forth in this section.

Section 4. Funding

Purpose:

- Maximum Compensation: It is expressly understood that the total compensation to be paid to Subrecipient under this Agreement for services rendered shall not exceed Sixty-Eight Thousand Two Hundred Eighty-Four Dollars ($68,284.00).

- All other covenants, terms, and conditions set forth in the Agreement and not amended by this Amendment shall remain in full force and effect as if fully set forth herein.

IN WITNESS WHEREOF, the undersigned, as authorized representatives of the City and Subrecipient have entered into this Agreement as of the date first written above.

CITY OF SALINAS

___________________________________

Rene Mendez, City Manager

APPROVED AS TO FORM:

___________________________________

□ Christopher A. Callihan, City Attorney

□ Rhonda Combs, Assistant City Attorney

CENTRAL COAST CENTER FOR INDEPENDENT LIVING

___________________________________

Judy Cabrera, Executive Director

https://salinasca.sharepoint.com/sites/HomelessProjectsTeam/Shared Documents/FY 24-25 Funding Agreements/CCCIL/SESG Funding Agreement Amendment-6.4.24.docx